## Slide 1: Why Monitor and Evaluate Programmes?
MODULE 1

## Slide 2: The Power of Data
Initiating a Programme
Secure $$
Implement
End Project Cycle
Continue Project?
Needs Assessment
Qualitative data/ Stories
Set Baseline
Fundraise/
Proposal Writing
Target Setting
Logframe
Review Coverage
Map Regularly
Review Project Cost Efficiencies/ Absorption
Re-evaluate Needs
Qualitative data/ Stories
Set Baseline
Evaluate
Relevance,
Effectiveness
Efficiency
Impact
Sustainability
Notes: *Setting the baseline
*Target setting
The five OECD/DAC evaluation criteria of Relevance, Effectiveness, Efficiency, Impact and Sustainability are covered, ∎ cross-cutting issues, such as poverty, gender and environment, are taken into consideration4, ∎ and the intervention logic (e.g. Logframe) is analysed.

## Slide 3: Data is Essential to develop future funding proposals!
Assess your program and identify gaps
Develop strategies to address those gaps and improve your program
Report on program progress
Share successes and challenges
Notes: *Setting the baseline
*Target setting
The five OECD/DAC evaluation criteria of Relevance, Effectiveness, Efficiency, Impact and Sustainability are covered, ∎ cross-cutting issues, such as poverty, gender and environment, are taken into consideration4, ∎ and the intervention logic (e.g. Logframe) is analysed.

## Slide 4: What is the difference between Monitoring and Evaluation?

## Slide 5
Outcome
Intervention
Monitoring is the routine tracking of program activities to help program and project managers measure progress.
Monitoring helps answer these questions:
  Are we completing activities according to plan?
  What are the costs?
  Who is using our services?
Evaluation is a specific study that helps determine program achievement.
A well-planned, high-quality evaluation can help answer:
  How well was the project implemented?
  Were the desired changes achieved?
  If the change was achieved, to what extent can it be attributed to the project?
Notes: 5
From MEASURE Eval: What is the difference between monitoring and evaluation? Monitoring and evaluation are related, but distinct, concepts. This slide helps us clarify what question we can answer through monitoring and what types of questions we can answer through evaluation. [READ SLIDE]
The important distinction is that monitoring ensures that you are doing what you said you were going to do and helps you make corrections as you implement your program. In contrast, evaluation helps you determine whether you achieved the desired outcomes and, eventually, impact. Note that routine monitoring occurs during the intervention and evaluation is generally used to determine progress towards outcomes.

## Slide 6: Key Terms in M&E (1)
Goal
Objective
Intervention/
Activity/
Process
Logic Model
Indicator
Output
Broad statement of a desired, long-term outcome of the program
Statements of desired, specific, measurable, appropriate, realistic and time bound program results
Services that the program/ project provides to accomplish its objectives
Program design, management, and evaluation tool that describes the main elements of a program and how these elements work together
Variable that measures one aspect of a program/ project or outcome
Indicator of activity or immediate result of your program process
Notes: SEE GLOSSARY HANDOUT: MEASURE EVALUATION AND UNAIDS
End-of-project target: A measure (number, %, product you hope to meet) What level/change to you expect to see at program conclusion?

## Slide 7: Key Terms in M&E (2)
Outcome
Result
Impact
Frequency
Baseline
Data Source
Indicator of changes in knowledge, attitudes, and practices that help demonstrate achievement of objectives
Benchmark progress result that you will measure along the way to achieving your objectives
Long term results of one or more programs over time; population-level changes
Data source: Where will you get this data? Will you collect it? Or your implementing partner?
How often will you collect or report this information?
What is the current level of this knowledge/
attitude/practice in your target area?
Notes: SEE GLOSSARY HANDOUT: MEASURE EVALUATION AND UNAIDS
End-of-project target: A measure (number, %, product you hope to meet) What level/change to you expect to see at program conclusion?

## Slide 8: Simple Logic Model – HIV/AIDS Program
Monitoring |  |  | Evaluation | 
Inputs | Process/Activity/ Intervention | Outputs | Outcome | Impact
Funds Supplies/drugs Equipment Policies, guidelines and procedures | Training HIV Testing ARV Treatment Services | #Trained staff on gender responsive OST # WID receiving HIV testing & referred to ART # WID referred to NGO peer support # pregnant WID receiving PMTCT prescription | Improved provider attitudes Increased skills and knowledge Decreased discrimination Enhanced quality of life | Reduced incidence of HIV Reduced HIV related morbidity Reduced Mortality rate/life expectancy
Notes: UNAIDS, WHO, UNICEF, FHI, MEASURE Evaluation, USAID. (2004). National AIDS programmes: A guide to monitoring and evaluating HIV/AIDS care and support. WHO.

## Slide 9: Indicators and Monitoring
How Well are We Doing?

## Slide 10: Example: M&E Questions for HIV Outreach Programs (1)
Are Outreach activities/services being provided as planned?
Are there minimum quality standards/standard operating procedures in place or program requirements? Are they being met?
Are outreach encounters increasing?
Notes: This slide illustrates some of the questions that M&E of HIV Outreach programs (CAN BE IVDU, CSW, MSM PROGRAMS ETC.) are likely to need to address at different levels. If you are a program manager, you may be interested in the delivery process. That is, you will want to monitor the volume and type of outreach that is being provided, whether the services are being provided as planned, whether services meet minimum standards of quality . To do this, you may implement an information system to help describe and monitor process indicators for outreach. As the manager of the national program, however, you may be less interested in the details of the process and be more interested in tracking whether the outreach is effective, increasing encounters and whether more people are accessing the desired services, prevention and care. In addition, as the expected outcomes of your program are to reduce HIV risk behaviors and increase the use of prevention, care, support and treatment services by those who are infected, you may also want to monitor these behaviors. While there are many factors that can affect behaviors, you may also want to know whether or not there is behavior change among clients who have received outreach services. These are evaluation questions as they are really asking whether or not counseling and testing services are effective in changing behavior. While changes in behavior can be monitored through behavioral surveillance, attributing these changes to the program is part of program evaluation and requires more rigorous data collection methodologies and analyses.

## Slide 11: Example: M&E Questions for HIV Outreach Programs (2)
Are there disparities among different types of clients being reached?
Are the scale and type of outreach activities sufficient given the size and scale of the epidemic, geographic area, target population?
How successful is Outreach as an entry point for HIV prevention, care, support and treatment services?
Notes: This slide illustrates some of the questions that M&E of HIV Outreach programs (CAN BE IVDU, CSW, MSM PROGRAMS ETC.) are likely to need to address at different levels. If you are a program manager, you may be interested in the delivery process. That is, you will want to monitor the volume and type of outreach that is being provided, whether the services are being provided as planned, whether services meet minimum standards of quality . To do this, you may implement an information system to help describe and monitor process indicators for outreach. As the manager of the national program, however, you may be less interested in the details of the process and be more interested in tracking whether the outreach is effective, increasing encounters and whether more people are accessing the desired services, prevention and care. In addition, as the expected outcomes of your program are to reduce HIV risk behaviors and increase the use of prevention, care, support and treatment services by those who are infected, you may also want to monitor these behaviors. While there are many factors that can affect behaviors, you may also want to know whether or not there is behavior change among clients who have received outreach services. These are evaluation questions as they are really asking whether or not counseling and testing services are effective in changing behavior. While changes in behavior can be monitored through behavioral surveillance, attributing these changes to the program is part of program evaluation and requires more rigorous data collection methodologies and analyses.

## Slide 12: How do we answer these questions?
THROUGH OUR MONITORING ACTIVITIES AND ASSESSING OUR INDICATORS OVER TIME

## Slide 13: Role of an Indicator
Indicators represent(s) key or significant program areas which demonstrate change (or lack of)
Indicators track trends over time (positive or negative, “up or down”)
Indicators are specific information that provide evidence as to the achievement of (or lack of) results and activities.
Straightforward, clear and realistic
Notes: Ask for examples, share examples of some indicators…rapid testing and incidence…good few indicators, BE STRATEGIC don’t go overboard!!!!

## Slide 14: Why are Indicators Important?
Enables us to reduce large amount of data down to its simplest form (e.g percent of clients who tested after receiving pre-test counseling, percent of WID receiving counseling, prevalence rate).
When compared with targets or goals, indicators can:
  signal the need for corrective management
  evaluate the effectiveness of various management actions
  provide evidence as to whether objectives are being achieved
  through disaggregation, will provide information on sub-groups, such as gender, age groups, etc.
Notes: National level indicators and program indicators – both … understand there is a difference…

## Slide 15: Expressing an Indicator (1)
Number
Ratio
Percentage
Average
Rate
Index (composite of indicators)
An indicator is usually expressed in numerical form
Notes: 6

## Slide 16: Expressing an Indicator (2)
An indicator can also be expressed in non-numerical form such as in words
Non-numerical indicators are also referred to as qualitative or categorical indicators